## Sheet1
Legend
| CMPUT301W18T14 |  | Planned Work
| Release Planning |  | Actual Work
|  | February | [14 empty] | Project Part 2 | [9 empty] | Project Part 3 |  |  | March | [17 empty] | Project Part 4 | [12 empty] | April | [7 empty] | Project Part 5
|  | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W
# | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
2 | Project Part 2
2.1 | Use Cases | bar: February S 10 to February R 15
2.2 | UI Mockup and Storyboard | bar: February S 10 to February R 15
2.3 | Release Planning | bar: February S 10 to February R 15
2.4 | Glossary and Information Sources | bar: February S 10 to February R 15
3 | Project Part 3
3.1 | Address Feedback
3.1a | Mockup Feedback | bar: Project Part 2 R 22
3.1b | Release Plan Feedback | bar: Project Part 2 F 23 to Project Part 2 S 25
3.2 | Object Oriented Analysis and Design
3.2a | Team Meeting for Initial Draft | bar: Project Part 2 R 22
3.2b | Uploading to LucidChart/extend ideas | bar: Project Part 2 R 22 to Project Part 2 S 25
3.3b | Final Review | bar: Project Part 2 S 25
3.3 | Test Cases
3.3a | Initial Test Cases | bar: Project Part 2 R 22 to Project Part 2 S 25
3.3b | Final Review | bar: Project Part 2 S 25
3.4 | Final Testing and Review | bar: Project Part 2 S 25 to Project Part 3 M 26
4 | Project Part 4
4.1 | Address Feedback
4.1a | Lab Feedback | bar: Project Part 3 W 28; March W 7; March W 14
4.1b | End of Project Part 3 Feedback | bar: March M 5 to March W 7
4.2 | Code Base of Prototype
4.2a | 50% Features Complete | bar: Project Part 3 T 27 to March W 14
4.2b | Code Reviews | bar: March M 5; March M 12; March R 15 to March F 16
4.2c
4.3 | Code Documentation
4.3a | Javadoc | bar: March M 12 to March F 16
4.4 | Test Cases
4.4a | JUnit Testing | bar: March R 15 to Project Part 4 M 19
4.5 | Object Oriented Design
4.5a | Update UML Diagram | bar: March M 12 to March F 16
4.6 | Release Planning
4.6a | Update Release Plan for Part 5 | bar: March F 16 to Project Part 4 M 19
Review Part 4 Progress | bar: March W 14 to March S 17
4.7 | Reuse Statement
4.7a | Created documentation for software reuse | bar: March R 15 to Project Part 4 M 19
(NOTE However, rights will be obtained as we go)
5 | Project Part 5
5.1 | Address Feedback
5.1a | Lab Feedback | bar: Project Part 4 W 21; Project Part 4 W 28; April T 3
5.1b | End of Project Part 4 Feedback
5.2 | Code Base of Prototype
5.2a | Remaining Features | bar: Project Part 4 T 20 to April S 1
5.2b | Code Reviews | bar: Project Part 4 M 26; April M 2; April W 4 to April R 5
5.3 | Code Documentation
5.3b | Javadoc | bar: April M 2 to April R 5
5.4 | Test Cases
5.4a | JUnit Testing | bar: April T 3 to April S 7
5.5 | Requirements Specification
5.5a | Updated Use Case | bar: April M 2 to April T 3
5.6 | Object Oriented Design
5.6a | Update UML diagram | bar: April M 2 to April R 5
5.7 | Release Planning
5.7a | Evaluate Part 5 Progress | bar: April M 2 to April W 4
5.7b | Update progress on Release Planning | bar: April R 5 to April S 7
5.8 | Reuse Statement
5.8a | Update documentation for software reuse | bar: April M 2 to April F 6
(NOTE However, rights will be obtained as we go)
5.9 | Demo Presentation
5.9a | Demo Presentation in the lab | bar: Project Part 5 W 11
5.1 | Promotional Video
5.10a | Create promotional video | bar: April W 4 to April R 5