## Sheet1
Overview
Week | Project Part | Use Case or Description | Related Artifacts (if any)
Week 1 | Project Part 2 | Finish Use Cases
Finish User Interface Mockup and Storyboard
Finish Release Plan
Finish Glossary
Week 2 | Project Part 3 | Respond to feedback
Finish UML
Create test cases for entity classes
Week 3 | Project Part 4 | 1: Authenticate | US 03.01.01
|  | 2: Create Account | US 03.01.01
|  | 17: Search for Available Tasks | US 04.01.01, US 04.02.01
|  | 5: Add Task | US 01.01.01, US 02.02.01, US 08.01.01
|  | 6: View My Task | US 01.02.01, US 08.01.01
|  | 9: View Task Details | US 01.02.01
Week 4 |  | Testing and revisions based on feedback
|  | 7: Edit One of My Tasks | US 01.03.01, US 08.01.01
|  | 8: Delete One of My Tasks | US 01.04.01, US 08.01.01
|  | 18: Add Task Photograph | US 09.01.01, US 09.03.01
|  | 19: View Task Photograph | US 09.02.01
|  | 4: View User Contact Info | US 03.03.01
Week 5 |  | Testing and revisions based on feedback
|  | 10: Make a Bid | US 05.01.01
|  | 11: Task Provider Views List Of Tasks | US 05.02.01
|  | 13: Task Requestor Views Tasks Bidded On | US 05.04.01
|  | 14: Task Requestor Views Bids On Task | US 05.05.01, US 05.04.01
Week 6 | Project Part 5 | Testing and revisions based on feedback
|  | 15: Task Requestor Accepts Bid On Task | US 05.06.01
|  | 16: Task Requestor Declines Bid | US 05.07.01
|  | 12: Task Requestor Notification | US 05.03.01
|  | 26: Wow factor | US Wow Factor
Week 7 |  | Testing and revisions based on feedback
|  | 25: Change status for one of my tasks | US 07.01.01, US 07.02.01
|  | 23: View Task Assigned | US 06.01.01
|  | 24: View Task with Status Assigned | US 06.02.01
|  | 20: Geolocation Set | US 10.01.01
Week 8 |  | Testing and revisions based on feedback
|  | 21: Geolocation View | US 10.02.01
|  | 3: Edit Profile | US 03.02.01